## Sheet1
78 | 78 | 78 | 56 | 77 | 20 | 78 | 8 | 77
FUZE Project ID | Project Alt.Name | Address | Activation/Withdraw Milestone (F) | Inservice Activation (A) | Construction Started (F) | Construction Started (A) | Construction Completed Milestone (F) | Construction Completed Milestone (A)
15011371 | NNJ HOBOKEN NODE 101 | 875 Madison St | 2019-06-28 | 2019-06-28 |  | 2018-07-03 |  | 2019-06-07
12439036 | NNJ HOBOKEN NODE 103 | 942 Willow Ave - Pole located on 10th St near NE corner of parcel - South side of 10th St | 2020-03-13 | 2020-03-13 |  | 2019-09-30 | 2020-01-29 | 2021-06-29
12439038 | NNJ HOBOKEN NODE 104 | 1001 Garden Street |  | 2019-10-17 | 2019-07-26 | 2019-07-26 |  | 2019-10-01
12439040 | NNJ HOBOKEN NODE 105 | 1026 Bloomfield Street | 2019-12-19 | 2019-12-19 |  | 2019-09-06 |  | 2019-12-02
15011471 | NNJ HOBOKEN NODE 107 | 397 10th St |  | 2019-06-28 | 2018-04-27 | 2018-04-26 |  | 2019-06-07
15857917 | NNJ HOBOKEN NODE 109 | 1101 Adams St - East side of road | 2020-03-19 | 2020-03-19 |  | 2020-01-08 |  | 2020-01-13
12439050 | NNJ HOBOKEN NODE 110 | 1130 Clinton St - West side of road | 2020-02-28 | 2020-02-28 |  | 2020-01-09 |  | 2020-01-13
12439052 | NNJ HOBOKEN NODE 111 | 1140 Garden St. | 2020-03-18 | 2020-03-18 |  | 2019-09-20 |  | 2020-01-06
12439054 | NNJ HOBOKEN NODE 112 | 107 13th Street | 2019-12-22 | 2019-12-22 |  | 2019-09-26 |  | 2019-12-13
12439056 | NNJ HOBOKEN NODE 113 | 1200-22 Willow Ave. |  | 2019-11-11 | 2019-07-09 | 2019-07-09 |  | 2019-10-01
15019379 | NNJ HOBOKEN NODE 114 | 393 13th St |  | 2019-08-30 | 2019-04-09 | 2019-04-09 |  | 2019-08-02
12439062 | NNJ HOBOKEN NODE 115 | 1200 Madison Street | 2019-09-26 | 2019-09-26 |  | 2019-06-19 |  | 2019-09-03
12439064 | NNJ HOBOKEN NODE 116 | 1240 Park Ave. |  | 2019-12-19 | 2019-09-10 | 2019-09-05 |  | 2019-12-02
12439066 | NNJ HOBOKEN NODE 117 | 1330 Clinton Street | 2019-11-11 | 2019-11-11 |  | 2019-07-26 |  | 2019-10-16
12439068 | NNJ HOBOKEN NODE 118 | 1316 Garden Street | 2020-03-18 | 2020-03-18 |  | 2019-09-26 |  | 2020-01-06
12439070 | NNJ HOBOKEN NODE 119 | 1404 Willow Ave. | 2019-12-19 | 2019-12-19 |  | 2019-09-04 | 2019-12-02 | 2019-12-19
15857925 | NNJ HOBOKEN NODE 120 | 1516-1532 Park Ave - South side of road | 2020-04-22 | 2020-04-22 |  | 2020-04-14 |  | 2020-04-14
2560063 | NNJ HOBOKEN ODAS 066 | 328 Adams street | 2019-09-27 | 2019-09-27 |  | 2019-06-27 |  | 2019-08-19
2560070 | NNJ HOBOKEN ODAS 067 | 330 Grand Street |  | 2019-09-27 | 2018-04-30 | 2018-04-30 |  | 2019-09-06
15858499 | NNJ HOBOKEN NODE 068 | 300 Clinton St - West side of road | 2020-02-28 | 2020-02-28 |  | 2019-09-30 |  | 2020-01-23
2560073 | NNJ HOBOKEN ODAS 069 | 308 Willow Ave |  | 2019-10-18 |  | 2019-06-27 |  | 2019-09-16
2560074 | NNJ HOBOKEN ODAS 070 | 215 Adams Street | 2019-08-14 | 2019-08-14 |  | 2018-06-29 |  | 2019-06-07
2560151 | NNJ HOBOKEN ODAS 071 | 308 2nd Street |  | 2018-12-10 |  | 2018-05-08 |  | 2018-11-26
15857889 | NNJ HOBOKEN NODE 072 | 551 Observer Highway - Pole located on north side of Newark St | 2020-04-22 | 2020-04-22 |  | 2019-09-30 |  | 2020-04-13
12438970 | NNJ HOBOKEN NODE 073 | 61-89 Willow Ave. | 2019-12-19 | 2019-12-19 |  | 2019-09-09 |  | 2019-12-13
2590037 | NNJ HOBOKEN NODE 074 | 391 Newark Ave. | 2019-12-31 | 2019-12-31 |  | 2019-09-18 |  | 2019-12-27
12438976 | NNJ HOBOKEN NODE 075 | 58 Monroe Street |  | 2019-10-24 | 2019-07-09 | 2019-07-09 |  | 2019-10-07
12438978 | NNJ HOBOKEN NODE 076 | 102 Jefferson street | 2020-01-23 | 2020-01-23 |  | 2019-09-23 |  | 2019-12-18
15857911 | NNJ HOBOKEN NODE 078 | 651 First St - South side of road | 2020-02-28 | 2020-02-28 |  | 2020-01-07 |  | 2020-01-13
12438988 | NNJ HOBOKEN NODE 081 | 130 Madison Street | 2020-01-15 | 2020-01-15 |  | 2019-09-30 |  | 2019-12-26
15014545 | NNJ HOBOKEN NODE 082 | 215 Monroe St. |  | 2018-12-18 | 2018-03-26 | 2018-03-26 |  | 2018-12-14
15009595 | NNJ HOBOKEN NODE 083 | 279 Jackson St. |  | 2019-08-27 |  | 2019-04-10 |  | 2019-08-02
12438996 | NNJ HOBOKEN NODE 084 | 700 First St - Pole located on 2nd St near NW corner of parcel South side of 2nd St | 2020-04-24 | 2020-04-24 |  | 2019-12-11 | 2020-01-06 | 2022-03-01
12439000 | NNJ HOBOKEN NODE 086 | 308 Jefferson Street | 2019-12-19 | 2019-12-19 |  | 2019-06-28 | 2019-09-16 | 2021-12-21
16375074 | NNJ Hoboken Node 087 - MKT 87 - MODIFICATION | 400 Madison St | 2021-10-25 | 2021-10-25 | 2021-10-25 | 2021-10-25 | 2021-10-25 | 2021-10-25
12439006 | NNJ HOBOKEN NODE 089 | 500 Jefferson Street | 2019-09-27 | 2019-09-27 |  | 2019-06-21 |  | 2019-08-16
12439008 | NNJ HOBOKEN NODE 090 | 414 Marshall Drive |  | 2019-10-29 | 2019-06-20 | 2019-06-20 |  | 2019-09-16
12439014 | NNJ HOBOKEN NODE 092 | 611 Madison St |  | 2019-10-29 | 2019-07-25 | 2019-07-03 |  | 2019-09-10
12439016 | NNJ HOBOKEN NODE 093 | 650 6th St. | 2019-12-16 | 2019-12-16 |  | 2019-09-24 |  | 2019-12-10
12439018 | NNJ HOBOKEN NODE 094 | 719 Monroe St | 2019-12-16 | 2019-12-16 |  | 2019-09-24 |  | 2019-12-13
12439020 | NNJ HOBOKEN NODE 095 | 710 Jefferson St. | 2019-12-04 | 2019-12-04 |  | 2019-09-30 |  | 2019-12-02
12439022 | NNJ HOBOKEN NODE 096 | 614 Clinton Street | 2019-10-18 | 2019-10-18 |  | 2019-07-12 | 2019-09-10 | 2022-02-03
12439024 | NNJ HOBOKEN NODE 097 | 701 Adams Street | 2019-12-20 | 2019-12-20 |  | 2019-09-24 | 2019-12-02 | 2019-12-19
12439028 | NNJ HOBOKEN NODE 099 | 104 10th Street | 2019-12-19 | 2019-12-19 |  | 2019-09-30 |  | 2019-12-13
2453384 | NNJ HOBOKEN ODAS 008 - C | 1200 Hudson St |  | 2019-11-01 | 2018-07-02 | 2018-07-02 |  | 2019-10-21
2457691 | NNJ HOBOKEN ODAS 009 | 1122 Hudson St |  | 2019-12-18 | 2018-07-05 | 2018-07-05 |  | 2019-12-02
2458037 | NNJ HOBOKEN ODAS 011 | Frank Sinatra Dr. (across from Elysian Park) |  | 2018-07-05 | 2017-12-12 | 2017-12-12 |  | 2018-06-16
15857645 | NNJ HOBOKEN NODE 012 | East side of Hoboken Shore Road - Frank Sinatra Drive |  | 2020-04-24 | 2019-12-13 | 2020-01-27 |  | 2020-01-27
15836915 | NNJ HOBOKEN ODAS 013 | 834 Hudson Street - west side of road | 2020-02-26 | 2020-02-26 |  | 2019-09-26 |  | 2019-12-26
15857657 | NNJ HOBOKEN NODE 018 | 164 Fifth St - North side of road | 2020-02-27 | 2020-02-27 |  | 2019-09-30 |  | 2020-01-06
2458708 | NNJ HOBOKEN ODAS 020 | 525 Court Street |  | 2018-06-19 | 2017-12-11 | 2017-12-11 |  | 2018-05-08
15857933 | NNJ HOBOKEN NODE 021 | 301 Washington St - Pole located on 3rd St near south entrance of parking lot - north side of 3rd St | 2020-04-03 | 2020-04-03 |  | 2019-09-30 |  | 2020-01-28
15857835 | NNJ HOBOKEN ODAS 027 | 210-222 River St - Marine View Plaza - West side of road | 2020-08-10 | 2020-08-10 |  | 2020-02-25 |  | 2020-03-19
2458771 | NNJ HOBOKEN ODAS 038 | 40 7th Street | 2020-03-18 | 2020-03-18 |  | 2019-09-24 |  | 2020-01-06
2501467 | NNJ HOBOKEN ODAS 041 | 726 Bloomfield Street |  | 2019-12-19 | 2018-07-06 | 2018-07-06 |  | 2019-12-02
2501471 | NNJ HOBOKEN ODAS 042 | 533 Bloomfield Street | 2019-10-15 | 2019-10-15 |  | 2019-07-01 |  | 2019-09-24
2501488 | NNJ HOBOKEN ODAS 043 | 320 Bloomfield Street | 2019-11-26 | 2019-11-26 |  | 2019-07-15 |  | 2019-11-07
2501495 | NNJ HOBOKEN ODAS 044 | 120 Bloomfield Street | 2019-09-27 | 2019-09-27 |  | 2019-06-24 |  | 2019-08-21
2501496 | NNJ HOBOKEN ODAS 045 | 77 Bloomfield Street | 2019-09-26 | 2019-09-26 |  | 2019-07-01 |  | 2019-09-10
15344289 | NNJ HOBOKEN ODAS 046 | 730 Garden Street | 2019-12-19 | 2019-12-19 |  | 2019-07-17 |  | 2019-10-01
2514947 | NNJ HOBOKEN ODAS 047 | 733 Park Avenue | 2019-09-27 | 2019-09-27 |  | 2019-06-28 |  | 2019-09-13
15347931 | NNJ HOBOKEN ODAS 048 | 527 Garden Street | 2019-11-04 | 2019-11-04 |  | 2019-07-17 |  | 2019-10-01
2515556 | NNJ HOBOKEN ODAS 049 | 517 Park Avenue | 2019-10-15 | 2019-10-15 |  | 2019-07-18 |  | 2019-09-13
2515557 | NNJ HOBOKEN ODAS 050 | 333 Garden Street | 2019-11-19 | 2019-11-19 |  | 2019-07-25 |  | 2019-11-07
2515558 | NNJ HOBOKEN ODAS 051 | 526 Clinton Street |  | 2019-10-18 | 2019-07-26 | 2019-07-23 |  | 2019-10-07
2501566 | NNJ HOBOKEN ODAS 052 | 274 4th Street | 2020-07-22 | 2020-07-22 |  | 2020-03-26 |  | 2020-06-12
2515559 | NNJ HOBOKEN ODAS 053 | 510 Grand Street | 2019-12-19 | 2019-12-19 |  | 2019-07-24 |  | 2019-12-02
15347933 | NNJ HOBOKEN ODAS 054 | 526 Adams St | 2019-12-12 |  |  | 2019-09-17 |  | 2019-12-02
2501504 | NNJ HOBOKEN ODAS 055 | 162 2nd Street | 2019-12-19 | 2019-12-19 |  | 2019-09-23 |  | 2019-12-10
15347941 | NNJ HOBOKEN ODAS 057 | 80 Park Ave | 2019-12-23 | 2019-12-23 |  | 2019-09-30 |  | 2019-12-10
2515561 | NNJ HOBOKEN ODAS 058 | 115 Clinton Street | 2019-09-26 | 2019-09-26 |  | 2019-06-26 |  | 2019-09-09
15347975 | NNJ HOBOKEN ODAS 059 | 95 Willow Avenue | 2019-12-19 | 2019-12-19 |  | 2019-06-25 |  | 2019-09-10
2515563 | NNJ HOBOKEN ODAS 060 | 126 Grand Street | 2019-12-19 | 2019-12-19 |  | 2019-09-23 |  | 2019-12-02
2512737 | NNJ HOBOKEN ODAS 061 | 302 Park Avenue | 2020-02-27 | 2020-02-27 |  | 2019-07-24 |  | 2019-10-07
15347979 | NNJ HOBOKEN ODAS 062 | 633 Willow Ave |  | 2019-10-25 | 2019-07-26 | 2019-07-25 |  | 2019-10-01
2515565 | NNJ HOBOKEN ODAS 063 | 244 9th Street |  | 2019-08-01 | 2018-04-27 | 2018-04-26 |  | 2019-07-12
2501561 | NNJ HOBOKEN ODAS 064 | 510 Willow Avenue | 2019-12-20 | 2019-12-20 |  | 2019-07-25 | 2019-10-01
15347981 | NNJ HOBOKEN ODAS 065 | 158 7th Street | 2019-12-06 | 2019-12-06 |  | 2019-09-30 |  | 2019-12-02